## Sheet1
# | Task | Status | Remarks | Timeline
|  |  |  | 2017-06-12 | 2017-06-19 | 2017-06-26 | 2017-07-03 | 2017-07-10 | 2017-07-17 | 2017-07-24 | 2017-07-31 | 2017-08-07 | 2017-08-14 | 2017-08-21 | 2017-08-28 | 2017-09-04 | 2017-09-11
1 | Change Assessment | In Process | Potential delay of one week (see red box in timeline section) | bar: 2017-07-31
1.1 | Current Situation Characterization | In Process | Progressing according to schedule | bar: 2017-06-12 to 2017-07-17
1.1.1 | Interviewing the major users of the current system | Completed | 22 Current users were interviewed
1.1.2 | Mapping out the current situation | In Process | Progressing according to schedule | bar: 2017-06-12 to 2017-07-10
1.2 | Assessing Required Changes | In Process | Potential delay of one week (see red box in timeline section) | bar: 2017-07-31
1.2.1 | Mapping the new system requirements | Completed | Link to the map document | bar: 2017-06-12 to 2017-06-19
1.2.2 | Approval of the new map | In Process | Progressing according to schedule
1.2.3 | Putting together a work plan for the new system | Not Started | Potential delay of one week (see red box in timeline section) | bar: 2017-07-17 to 2017-07-31
2 | Change Impacts | In Process | Progressing according to schedule
2.1 | Assessing who will be impacted | Completed | Link to the document | bar: 2017-06-19 to 2017-07-03
2.2 | Estimating the positive impacts on the company | Completed | Link to the document, completed ahead of time
2.3 | Presenting the impacts to the key stakeholders | Not Started | Planned to commence on the 18th of July 2017 | bar: 2017-07-17 to 2017-07-24
2.4 | Go / No-Go approval | Not Started
3 | Stakeholder Engagement | In Process | Progressing according to schedule | bar: 2017-07-03 to 2017-08-14
3.1 | Agreeing on the frequency of the initial status meetings | In Process | Progressing according to schedule
3.2 | Approving the format of the status reports | In Process | Progressing according to schedule | bar: 2017-07-17 to 2017-08-14
4 | Communication Plan | Not Started
4.1 | Agree on communication medium (E-mails, meetings, etc.) | Not Started | bar: 2017-07-17 to 2017-07-24
4.2 | Agree on frequency of communications | Not Started
5 | Change Readiness | Not Started | bar: 2017-07-24 to 2017-08-14
5.1 | Agree on entry and exit criteria for the CM | Not Started
5.2 | Assess whether the criteria above was met | Not Started | bar: 2017-07-31
5.3 | Communicate the findings and conclusion | Not Started
6 | Role Mapping | Not Started | bar: 2017-07-24 to 2017-08-21
6.1 | Assess current users and permissions | Not Started
6.2 | Map out the needed permissions for the new system for each role in the company | Not Started | bar: 2017-07-31 to 2017-08-21
7 | Documents and SOP's | Not Started
7.1 | Documents | Not Started | bar: 2017-08-07 to 2017-08-28
7.1.1 | Document the initial situation | Not Started
7.1.2 | Document the approval process of the change | Not Started | bar: 2017-08-14 to 2017-08-28
7.1.3 | Document the new processes / procedures and systems | Not Started
8 | SOP's | Not Started | bar: 2017-08-21 to 2017-08-28
8.1 | Write the new SOP | Not Started
8.2 | Approve the SOP | Not Started | bar: 2017-08-28
9 | Training | Not Started
9.1 | Write the training materials | Not Started | bar: 2017-08-07 to 2017-08-21
9.2 | Approve the materials | Not Started
9.3 | Conduct training sessions with new users | Not Started | bar: 2017-08-21 to 2017-09-04
10 | Hypercare | Not Started
10.1 | Conduct extensive support for the new users | Not Started | bar: 2017-09-04 to 2017-09-11