## Slide 1
Change ID | <Change ID which can be a sequence number>
Change Requestor | <The person who has requested the change>
Change Documented By | <The person who has documented this change request. Generally the project manager>
Change Description | <A detailed description of the change. Provide as much details possible>
Change Impact | Scope Impact : <Explain if any impacts on the schedule> Scope Impact : <Explain if any impacts on the scope> Budget Impact : <Explain if impact on budget> Quality Impact : <Explain any quality impacts> Other Impacts : <Any other impacts of the change>
Options | <Suggest the options the stakeholders need to know>
Change Approved Date | <Date when the change was approved>
Change Approved By | <Document who approved the change - Very important>
Change Request Template

## Slide 2
Change ID | 0001
Change Requestor | Mr XYZ
Change Documented By | Swapnil Wale
Change Description | The development missed out estimating one of the components during the initial estimations. The requirements indicate that this functionality is a critical deliverable for the project.
Change Impact | Schedule Impact : If this change request is incorporated into the project schedule the project delivery will be delayed by 2 months. Scope Impact : None. Budget Impact : The budget will increase by $150,000 as the schedule will stretch by 8 weeks and the resources will remain of the project for a longer time. Quality Impact : None. Other Impacts : External clients will need to be communicated about the delay. Internal project XYZ will be impacted as requires will remain on this project for a longer time.
Options | Option 1: Approve the change request and extend the project for two months. Option 2: With option 1 if additional resources are added to the project the schedule impact can be minimised but the budget impact will increase to $250,000. Option 3: Deliver the project without the component in question and schedule the reminder of work as a different project. Note: The project team recommends option 2.
Change Approved Date | 12-12-2014
Change Approved By | Project Sponsor
Change Request Template (Example)