## Sheet1
Change Request Form
Project Name | Generico | Requested by | Hector Mendoza Jr.
Date of Request | 2017-12-04 | Change Number | 175-DGT
Description of Change
Add a pool to the hotel's design. The pool will be heated and indoor, and have a diving board 1.5 meters above the water level. Its dimensions will be 40X25X4 Meters.
Reason for Change Request
A recent questionnaire performed on 500 recent guests of other branches of the hotel revealed that a pool is the among the highest requested amenities by the guests.
Expected Effect on Deliverables
The approved design will be delayed by 3 weeks.
Expected Effect on the Timeline
The addition of the pool will delay the completion of the hotel's construction by 3 months, if approved by end of January 2018.
Expected Cost of Change
Hours | Architecture: 8 / Construction: 220 | Hourly Rate | Architecture: $70 / Construction: $22
Materials | $15,000 | Software | N/A
Misc. | N/A | Subtotal | $20,400
Status
Received On | 2017-12-05 | Approved by | Sheila DeWalt
Approved (Yes / No) | Yes | Approved on | 2017-12-08