## ITIL
RFC (Request for Change) Form - ITIL Template
General
RFC Number | ITIL-DRP-3340 | Requested by | Lars Christensen (SW TL)
Date of Request Submission | 2017-12-04 | Due Date for Approval | 2017-12-12
CI's (Configuration Items) to be Added / Modified / Removed
The operating system of a C&C (Command and Control) room needs to be modified to include multiple threats tracking capabilities. Currently the system can track only one threat at a time, and in case of a coordinated attack it will be futile.
Business Justification for RFC
Our clients realize that single threat tracking is useless in case of a diversion attack, and it will put us at a great disadvantage in comparison with our competitors if it isn't a part of the standard package.
Estimated Impact on the Business
High: The marketing division estimated that this modification will increase our sales by 34%. The cost - benefit analysis was positive, and concluded that the modified OS will enable us to penetrate new markets which are under the threat of terrorist attacks (and not conventional army attack threat).
Change Category
Choose one of the following - * Minor change (Requires the PM's approval) * Standard change (Requires the COO's approval) * Major change (Requires the CEO's approval)
Risk Factors
Adding the multiple threat capabilities will require the addition of 2 months to the new SW update timeline, and may exceed the deadline of submitting an answer to the RFP of a major defence contract. This contract is valued at $400,000
Authorization Information
Received on | 2017-12-04 | Received by | Regina Prince (CEO)
Status (Approved / Declined) | Declined | Comments | Will be implemented in the next upgrade