## Log
Project Change Log Excel Template
Project Name: SAP Implementation
Basic Information
Updated on: | 2021-06-21 | Updated By: | Maya
Version Number: | #BB667 | Review Date: | 2021-07-22
Change Details
Change # | Change Request | Requested By | Date of Request | Impact | Status | Comments
1 | Component not estimated. | Nick | 2021-01-26 | High | In Process | Schedule impact of 2 months and budget impact of $150,000.
2 | UI Design Contract | Nanita | 2021-02-24 | Low | Approved | Budget Impact of $20,000.
3 | New Workflow Option | Elina | 2021-03-02 | Medium | Denied | Schedule impact of 1 week.
4 | Component estimation | Maya | 2021-04-24 | Medium | Approved
5 | UI Design | sarah | 2021-06-26 | Medium | In Process
6 | Workflow procedure | marry | 2021-06-24 | High | Withdrawn
Note on D7: Format: DD-MMM-YYYY