## Sheet1
Project Change Log Template
Change ID | Change Description | Requester | Date Raised | Decision | Decision Date | Comments
0001 | Component not estimated. | Maya | 2014-12-12 | Approved | 2021-01-12 | Schedule impact of 2 months and budget impact of $150,000.
0002 | UI Design Contract | sarah | 2015-04-12 | Pending | 2021-03-05 | Budget Impact of $20,000.
0003 | New Workflow Option | Nick | 2015-01-12 | Pending | 4/6/20221 | Schedule impact of 1 week.
0004 | Component estimation | Maya | 2014-12-12 | Approved | 2021-01-12 | Schedule impact of 2 months and budget impact of $150,000.
0005 | UI Design | sarah | 2015-04-12 | Pending | 2021-03-05 | Budget Impact of $20,000.
0006 | Workflow procedure | Nick | 2015-01-12 | Denied | 4/6/20221 | Schedule impact of 1 week.