## Implementation Issues
Project Implementation Issue Register
Issue # | Description | Severity | Owner | Status | Impact / Comments
1 | The allotted downtime window was insufficient to run all the test scripts, and we requested a 2-hour extension (which was approved) | High | Neel | Open
2 | The contract stated that the support for tier 2 issues is 24X6, while the client demanded we fix a port malfunction on Sunday | Low | Wale | Open | The malfunction caused delays with the timeline.
3 | No budget was allocated for logistical support, specifically transport of servers to the clients’ site | Medium | Wale | Open
4 | Different SOP’s were used by the back-office personnel | Medium | Swapnil | Open
5 | The release took 2 additional resources than what was planned. | Low | Swapnil | Closed
6 | Backup process failed on the day as there was an issue with the script | Medium | Swapnil | Open | The release delayed by 2 hours.
7 | Traffic delays caused the team to arrive later | High | Neel | Closed
8 | Confercence call facility went down for 45 mins. | High | Neel | Open | Stakeholders could not get updates.

## Data
Severity | Status
High | Open
Medium | Closed
Low | WIP