## Run Sheet
Project Implementation Task Sheet
Seq # | Date & Time | Task Description | Phase | Owner | Duration (mins) | Status | Notes
100 | 2019-05-25 11:00 | Send communcation to stakeholders | Pre | Neel | 10 | Done | Some email bounced back.
110 | 2019-05-25 11:10 | Install server config and desktop config for CR078 | Pre | Neel | 20 | Done
120 | 2019-05-25 11:30 | Reboot Server | Pre | Raj | 20 | Hold | Network connectivty issue
130 | 2019-05-25 11:50 | Reinstall package | Pre | Raj | 10 | Hold | Delayed because of Task 102
140 | 2019-05-25 12:00 | Test CR078 | Core | Raj | 30 | Hold | Delayed because of Task 103
150 | 2019-05-25 12:30 | Start Implementation of CR090 | Core | Raj | 50 | Hold | Delayed because of Task 104
160 | 2019-05-25 13:20 | Shutdown all systems | Core | Raj | 20 | To do
170 | 2019-05-25 13:40 | Backup all systems | Core | Raj | 20 | To do
180 | 2019-05-25 14:00 | Run build deplyment script | Core | Raj | 20 | To do
190 | 2019-05-25 14:20 | Capture and output to verify | Core | Raj | 35 | To do
200 | 2019-05-25 14:55 | Implement CR09 and CR45 config changes | Core | Sam | 20 | To do
210 | 2019-05-25 15:15 | Implement CR67 website changes | Core | Sam | 20 | To do
220 | 2019-05-25 15:35 | Reboot all systems | Core | Sam | 45 | To do
230 | 2019-05-25 16:20 | Perform basic testing of all changes - CR078, CR090, CR09, CR45 and CR67. | Core | Sam | 25 | To do
240 | 2019-05-25 16:45 | Send communcation to stakeholders | Post | Sam | 25 | To do
250 | 2019-05-25 17:10 | Verify Logs for on billing system | Post | Sam | 25 | To do
260 | 2019-05-25 17:35 | Delete all backup and install scripts form server | Post | Sam | 25 | To do
Formulas:
Date & Time = [Date & Time, row above] + TIME(0,[Duration (mins), row above],0)

## Instructions
1. The implementation plan should contain all the tasks to be done before, during and after the release.
2. Each step must have a number, duration and owner assigned.
3. The plan should be updated and circulated at least a few days before the release. Ideally, feedback should be sort from everyone a week before the actual implementation.
4. The status of the tasks should be updated as the release progresses to keep track of tasks.
5. Release manager is responsible to get updates from the team - it can be via a call or emial.

## Data
Release Phase | Status
Pre | Done
Post | Hold
Core | To do