## Risk Report
Release Risk Assesment
Basic Information |  |  | Release Scope | [5 empty] | Risk Meter
Release ID | ZOR1004 |  | 2445 | Transaction Backup |  | 8766 | Password length fix
Release Name | Project Gamma |  | 1221 | Purchase Survey Option |  | 9875 | Transaction commit logic update
Release Manager | Swapnil Wale |  | 4558 | Radio button for Gender |  | 9456 | DB Upgrade
Project Manager | Megan Wales |  | 3245 | Reboot VPN servers and patch |  | 2378 | Network Upgrade
Release Start Date | 2019-03-14 |  | 342 | Retail Branding Change
Release Finish Date | 2019-04-25 |  | 1244 | Upgrade SERT Micro service
|  |  | 7989 | City radio button to be mandatory
|  |  | 9889 | Address field to accept to numbers
|  |  | 4553 | Customer notification updates
|  |  | 1907 | Customer email to be mandatory
Risk Indicators
Technical Complexity | High | No. of Applications |  |  | Medium | Potential for post release issues |  | Low |  | Release Schedule | Critical
Voume of System Changes | Low | Release Duration |  |  | Medium | Risk of rollback |  | Low |  | Criticial Resource Unavailiablity | Critical
Customer Impact | Low | Risk of brand damage |  |  | Medium | Irreversable changes |  | Low |  | Criticial Resource Dependancy | Critical
Skillset Gap | Low | Rescoure Coverage |  |  | Critical | Risk of data loss |  | Low |  | Other factors | Critical
Low
Risk
High
Risk
Medium Risk

## Data
Risk Rating | Count | Wieght | Score
Critical | 5 | 3 | 15
High | 1 | 2 | 2
Medium | 3 | 1 | 3
Low | 7 | 0 | 0
| 48 |  | 20
|  |  |  | sev1 | sev2
Chart Details |  |  |  | 16 | 105
Score | 20 |  |  | 16 | 1
Max | 48 |  |  | 16 | 100
Total | 68 |  |  | 48