## Release Schedule
ID # | Task Description | Owner | Duration (days) | Status | Comments
1 | Development |  |  | Completed
1.1 | Deployment stages plan | Project Manager | 8 | Completed
1.2 | Deployment stages are approved | Client | 1 | Completed | Client sign-off is required
1.3 | Feature backlogs are set | SW TL | 12 | Completed
1.4 | Backlogs are approved | Client | 2 | Completed
1.5 | Backlog #0 is completed | SW TL | 15 | Completed
1.6 | Backlog #1 is completed | SW TL | 10 | Completed
1.7 | Backlog #2 is completed | SW TL | 15 | Cancelled
2 | Testing |  |  | In Process
2.1 | Testing batch #1 is completed | Testing QA | 20 | Completed
2.2 | Testing batch #2 is completed | Testing QA | 15 | Completed
2.3 | Testing batch #3 is completed | Testing QA | 18 | Cancelled
2.4 | Testing batch #4 is completed | Testing QA | 5 | In Process
2.5 | Testing completion sign-off | Client | 1 | In Process | Client sign-off is required
3 | Data Load |  |  | In Process
3.1 | Legacy systems load | Data Validation | 2 | In Process
3.2 | Client validation - legacy systems | Client | 2 | Not Started | Client sign-off is required
3.3 | Interfaces load | Data Validation | 5 | Not Started
3.4 | Client validation - Interfaces systems | Client | 3 | Not Started | Client sign-off is required
4 | Change Management |  |  | In Process
4.1 | Characterization of current roles | OCM team | 20 | In Process | Organizational Change Management
4.2 | Mapping of the new roles requirements | OCM team | 25 | In Process
4.3 | New requirements mapping approval | Client | 3 | Not Started | Client sign-off is required
4.4 | Training materials build | OCM team | 45 | In Process
4.5 | Training materials approval | Client | 20 | Not Started | Client sign-off is required
5 | Production go-live |  |  | Not Started
5.1 | End users can access the new system | Client | 1 | Not Started
5.2 | Hyper-care period | All teams | 35 | Not Started
6 | Project Sign-Off | Client | 1 | Not Started | Client sign-off is required