## Release Status Report
Release Status Report | [7 empty] | Release Manager |  | Swapnil Wale |  | Overall Release Status | Delay
[8 empty] | Status Date |  | 2019-02-10
Basic Information |  |  | Release Schedule | [6 empty] | Release Timeline
Release Date |  | 2019-05-25 | Phase |  |  | Start | Finish | Duration | Status
Project Manager |  | James K | Build and Test |  |  | 2019-08-01 | 2019-08-20 | 14 | Green
Scrum Master |  | Megan W | Build Implementation Plan |  |  | 2019-08-20 | 2019-08-25 | 4 | Green
Go/No-Go |  | 2019-05-20 | Trial Implementation Plan |  |  | 2019-07-28 | 2019-08-15 | 14 | Green
Release Start Time |  | 7:00 | Go Live Implementation |  |  | 2019-08-10 | 2019-08-25 | 10 | Green
Release Finish Time |  | 9:00
Release Scope | [10 empty] | Release Risks
ID | Description |  |  | Status | ID | Description |  |  |  | Status | Risk Description |  | Owner | Status
2445 | Transaction Backup |  |  | On Track | 8766 | Reboot VPN servers and patch |  |  |  | Off Track | There is a skillset gap in the team working on the change request. |  | Neel | Open
1221 | Email updates |  |  | On Track | 9875 | Reduce MAR space on servers |  |  |  | On Track
4558 | Retail Branding Change |  |  | Off Track | 9456 | Update GST Logic |  |  |  | Delay | The timing of the release may clash with other system changes. |  | John | Closed
3245 | Retail Discount Code Module |  |  | Off Track | 2378 | Upgrade SERT Micro service |  |  |  | On Track
342 | Purchase Survey Option |  |  | On Track | 8904 | City radio button to be mandatory |  |  |  | Off Track | The release build is not stable. |  | Neel | Open
1244 | Opt out email option |  |  | Delay | 1445 | Address field to accept to numbers |  |  |  | Off Track
7989 | Radio button for Gender |  |  | On Track
9889 | Mandatory fields script issue |  |  | On Track
Formulas:
Release Manager = NETWORKDAYS([Start],[Finish])
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Do not edit this column.

## Data
Release Status | Risks Indicator
On Track | High
Off Track | Med
Delay | Low