## Report
Daily Testing Status Update
Test Cases # |  | 150 |  |  | Open Defects |  | 8 |  | Status Date | 2019-05-26
Executed # |  | 115 | Executed % | 77% | Critical / High |  | 4 |  | QA Start Date | 2019-05-12
Pending # |  | 35 | Pending % | 23% | Medium |  | 3 |  | QA End Date | 2019-05-29
On Hold # |  | 8 | On Hold % | 5% | Low/Trivial |  | 1 |  | Overall Status | Concern
Open Defects
ID | Description |  |  |  | Opened | Severity | Status | Assignee | Comments
BUG001 | Screen freezes when user submit the form. |  |  |  | 2019-05-12 | Medium | Open | Neel
BUG010 | User experience slowness when login for the first time. |  |  |  | 2019-05-15 | High | Open | James
BUG005 | System not calculating the bank fees correctly. |  |  |  | 2019-05-16 | Critical | Open | Neel | Critical as it can reject a policy.
BUG006 | Service desk users cannot see their profile icon. |  |  |  | 2019-05-16 | Medium | Open | Shree | Workaround available using search.
BUG007 | Customers cannot update their phone numbers. |  |  |  | 2019-05-16 | Critical | Open | Shree | Critical as users cannot change contact details.
BUG011 | The systems incorrectly calculates the tax amount on summary. |  |  |  | 2019-05-18 | High | Open | Shree | A display issue. Underlying data is correct.
BUG116 | The auto generated email template does not have the right subject. |  |  |  | 2019-05-20 | Medium | Open | Neel
BUG117 | Alignment issue for the form buttons |  |  |  | 2019-05-20 | Trivial | Open | Navvy

## Ref Data
Overall | Severity | Status
On Track | Critical | Open
Concern | High | Closed
Delayed | Medium | Abandon
Low
Trivial