## Dashboard
Logo | Task Management Dashboard | [5 empty] | 3-Feb-20 to 13-Mar-20
|  | Project | Task | Manager | Start Date | End Date | Duration | Days comp. | Progress | Budget | Actual | 2020-02-20 | 2020-02-21 | 2020-02-22 | 2020-02-23 | 2020-02-24 | 2020-02-25 | 2020-02-26 | 2020-02-27 | 2020-02-28 | 2020-02-29 | 2020-03-01 | 2020-03-02 | 2020-03-03 | 2020-03-04 | 2020-03-05 | 2020-03-06 | 2020-03-07 | 2020-03-08 | 2020-03-09 | 2020-03-10 | 2020-03-11 | 2020-03-12 | 2020-03-13 | 2020-03-14 | 2020-03-15 | 2020-03-16 | 2020-03-17 | 2020-03-18 | 2020-03-19 | 2020-03-20
|  | Alpha | Task 1 | McFay | 2020-02-28 | 2020-03-10 | 8 | 3 | 37.5% | 96000 | 32256
|  |  | Task 2 | Wood | 2020-03-02 | 2020-03-12 | 9 | 4 | 44.44% | 513000 | 226233
|  |  | Task 3 | Ladd | 2020-02-20 | 2020-02-26 | 5 | 3 | 60% | 616000 | 401579
|  |  | Task 4 | Hirsch | 2020-02-19 | 2020-02-21 | 3 | 3 | 100% | 817000 | 807069
|  |  | Task 5 | Samora | 2020-02-21 | 2020-03-02 | 7 | 3 | 42.86% | 372000 | 173166
|  |  | Task 6 | McFay | 2020-02-24 | 2020-03-06 | 10 | 2 | 20% | 50000 | 8400
|  |  | Task 7 | Wood | 2020-02-24 | 2020-03-06 | 10 | 3 | 30% | 807000 | 262679
|  |  | Task 8 | Ladd | 2020-02-24 | 2020-02-26 | 3 | 1 | 33.33% | 691000 | 0
|  | Delta | Task 1 | Hirsch | 2020-03-02 | 2020-03-12 | 9 | 8 | 88.89% | 787000 | 727188
|  |  | Task 2 | Samora | 2020-03-02 | 2020-03-13 | 10 | 2 | 20% | 228000 | 47880
|  |  | Task 3 | McFay | 2020-02-17 | 2020-02-20 | 4 | 0 | 0% | 147000 | 0
|  |  | Task 4 | Wood | 2020-02-19 | 2020-02-28 | 8 | 5 | 62.5% | 338000 | 205123
|  |  | Task 5 | Ladd | 2020-02-24 | 2020-03-06 | 10 | 3 | 30% | 857000 | 305949
|  |  | Task 6 | Hirsch | 2020-02-25 | 2020-03-03 | 6 | 3 | 50% | 602000 | 322371
|  |  | Task 7 | Samora | 2020-02-25 | 2020-02-28 | 4 | 2 | 50% | 990000 | 451440
|  | Gemini | Task 1 | Hirsch | 2020-02-17 | 2020-02-21 | 5 | 2 | 40% | 218000 | 97337
|  |  | Task 2 | Samora | 2020-02-17 | 2020-02-24 | 6 | 3 | 50% | 393000 | 177440
|  |  | Task 3 | McFay | 2020-02-18 | 2020-03-02 | 10 | 4 | 40% | 86000 | 31046
|  |  | Task 4 | Wood | 2020-02-21 | 2020-03-04 | 9 | 3 | 33.33% | 732000 | 261324
|  |  | Task 5 | Ladd | 2020-02-17 | 2020-02-20 | 4 | 1 | 25% | 492000 | 116850
|  |  | Task 6 | Hirsch | 2020-02-20 | 2020-02-27 | 6 | 0 | 0% | 188000 | 0
|  |  | Task 7 | Samora | 2020-02-20 | 2020-02-28 | 7 | 3 | 42.86% | 180000 | 79380
|  |  | Task 8 | McFay | 2020-02-24 | 2020-02-28 | 5 | 2 | 40% | 582000 | 195231
|  |  | Task 9 | Wood | 2020-02-24 | 2020-03-05 | 9 | 1 | 11.11% | 562000 | 74746
|  |  | Task 10 | Ladd | 2020-02-24 | 2020-03-02 | 6 | 3 | 50% | 416000 | 175015
|  | Orion | Task 1 | Hirsch | 2020-02-18 | 2020-02-26 | 7 | 7 | 100% | 293000 | 273001
|  |  | Task 2 | Samora | 2020-02-17 | 2020-02-27 | 9 | 4 | 44.44% | 224000 | 57910
|  |  | Task 3 | McFay | 2020-02-18 | 2020-02-27 | 8 | 0 | 0% | 978000 | 0
|  |  | Task 4 | Wood | 2020-02-20 | 2020-02-28 | 7 | 3 | 42.86% | 932000 | 379157
|  |  | Task 5 | Ladd | 2020-02-21 | 2020-02-26 | 4 | 1 | 25% | 854000 | 322812
|  |  | Task 6 | Hirsch | 2020-02-21 | 2020-02-28 | 6 | 3 | 50% | 81000 | 38461
|  |  | Task 7 | Samora | 2020-02-24 | 2020-03-02 | 6 | 5 | 83.33% | 169000 | 136468
|  |  | Task 8 | McFay | 2020-02-25 | 2020-02-28 | 4 | 1 | 25% | 61000 | 12078
|  |  | Task 9 | Wood | 2020-02-27 | 2020-03-06 | 7 | 3 | 42.86% | 645000 | 273048
|  |  | Task 10 | Ladd | 2020-02-17 | 2020-02-19 | 3 | 3 | 100% | 68000 | 64987
|  | Vega | Task 1 | Hirsch | 2020-02-17 | 2020-02-28 | 10 | 5 | 50% | 839000 | 406974
|  |  | Task 2 | Samora | 2020-02-21 | 2020-02-27 | 5 | 4 | 80% | 729000 | 487139
|  |  | Task 3 | McFay | 2020-02-24 | 2020-03-03 | 7 | 3 | 42.86% | 826000 | 298186
|  |  | Task 4 | Wood | 2020-02-26 | 2020-03-05 | 7 | 2 | 28.57% | 895000 | 280583
|  |  | Task 5 | Ladd | 2020-02-28 | 2020-03-03 | 3 | 2 | 66.67% | 341000 | 129785
|  | Mega | Task 4 | Hirsch | 2020-03-06 | 2020-03-09 | 2 | 3 | 150% | 500000 | 450000
|  |  | Task 11 | Peter | 2020-03-05 | 2020-03-09 | 3 | 2 | 66.67% | 50000 | 40000
|  | Build | Task 1 | McFay | 2020-02-26 | 2020-02-26 | 1 | 1 | 100%
|  |  | Task 2 | Samora | 2020-02-25 | 2020-02-26 | 2 | 1 | 50%
|  | Sun Trade | Task 2 | Hirsch | 2020-02-28 | 2020-03-03 | 3 | 2 | 66.67%
|  |  | Task 11 | Michle | 2020-02-03 | 2020-02-03 | 1 | 1 | 100%
|  | Grand Total | [7 empty] | 20245000 | 8830291
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
44%
DASHBOARD
DATABASE
HELP
CONTACT
SETTING

## Workings (hidden)
Budget v Actual Doughnut & Bar Chart |  |  | Tasks Bar Chart |  |  | Overall Progress - Days Completed v Duration Doughnut Chart |  |  |  |  | Scroll bar position
| Actual | Budget | Not Started | 3 | =COUNTIF(Dashboard!J7:J52,"="&0) | Values |  | Doughnut Chart | % | Formula | 17
Bar Chart | 8830291 | 20245000 | In Progress | 37 | =COUNTIFS(Dashboard!J7:J52,"<>"&0,Dashboard!J7:J52,"<"&1) | Days completed | 123 | Days Completed | 44.24% | =J3/$J$4
Dougnut Chart | 43.62% | 56.38% | Completed | 5 | =COUNTIF(Dashboard!J7:J52,"="&1) | Duration | 278 | Days Remaining | 55.76% | =1-M3
|  | =1-B4 | Remaining | 40 | =F3+F2
|  |  | Total Tasks | 45 | =COUNTA(Dashboard!D7:D51)

## Database
Logo | Task Management Dashboard
|  | Project | Task | Manager | Start Date | Duration | End Date | Days completed | Progress | Budget | Actual
|  | Gemini | Task 1 | Hirsch | 2020-02-17 | 5 | 2020-02-21 | 2 | 40% | 218000 | 97337
|  | Gemini | Task 2 | Samora | 2020-02-17 | 6 | 2020-02-24 | 3 | 50% | 393000 | 177440
|  | Gemini | Task 3 | McFay | 2020-02-18 | 10 | 2020-03-02 | 4 | 40% | 86000 | 31046
|  | Gemini | Task 4 | Wood | 2020-02-21 | 9 | 2020-03-04 | 3 | 33.33% | 732000 | 261324
|  | Gemini | Task 5 | Ladd | 2020-02-17 | 4 | 2020-02-20 | 1 | 25% | 492000 | 116850
|  | Gemini | Task 6 | Hirsch | 2020-02-20 | 6 | 2020-02-27 | 0 | 0% | 188000 | 0
|  | Gemini | Task 7 | Samora | 2020-02-20 | 7 | 2020-02-28 | 3 | 42.86% | 180000 | 79380
|  | Gemini | Task 8 | McFay | 2020-02-24 | 5 | 2020-02-28 | 2 | 40% | 582000 | 195231
|  | Gemini | Task 9 | Wood | 2020-02-24 | 9 | 2020-03-05 | 1 | 11.11% | 562000 | 74746
|  | Gemini | Task 10 | Ladd | 2020-02-24 | 6 | 2020-03-02 | 3 | 50% | 416000 | 175015
|  | Orion | Task 1 | Hirsch | 2020-02-18 | 7 | 2020-02-26 | 7 | 100% | 293000 | 273001
|  | Orion | Task 2 | Samora | 2020-02-17 | 9 | 2020-02-27 | 4 | 44.44% | 224000 | 57910
|  | Orion | Task 3 | McFay | 2020-02-18 | 8 | 2020-02-27 | 0 | 0% | 978000 | 0
|  | Orion | Task 4 | Wood | 2020-02-20 | 7 | 2020-02-28 | 3 | 42.86% | 932000 | 379157
|  | Orion | Task 5 | Ladd | 2020-02-21 | 4 | 2020-02-26 | 1 | 25% | 854000 | 322812
|  | Orion | Task 6 | Hirsch | 2020-02-21 | 6 | 2020-02-28 | 3 | 50% | 81000 | 38461
|  | Orion | Task 7 | Samora | 2020-02-24 | 6 | 2020-03-02 | 5 | 83.33% | 169000 | 136468
|  | Orion | Task 8 | McFay | 2020-02-25 | 4 | 2020-02-28 | 1 | 25% | 61000 | 12078
|  | Orion | Task 9 | Wood | 2020-02-27 | 7 | 2020-03-06 | 3 | 42.86% | 645000 | 273048
|  | Orion | Task 10 | Ladd | 2020-02-17 | 3 | 2020-02-19 | 3 | 100% | 68000 | 64987
|  | Vega | Task 1 | Hirsch | 2020-02-17 | 10 | 2020-02-28 | 5 | 50% | 839000 | 406974
|  | Vega | Task 2 | Samora | 2020-02-21 | 5 | 2020-02-27 | 4 | 80% | 729000 | 487139
|  | Vega | Task 3 | McFay | 2020-02-24 | 7 | 2020-03-03 | 3 | 42.86% | 826000 | 298186
|  | Vega | Task 4 | Wood | 2020-02-26 | 7 | 2020-03-05 | 2 | 28.57% | 895000 | 280583
|  | Vega | Task 5 | Ladd | 2020-02-28 | 3 | 2020-03-03 | 2 | 66.67% | 341000 | 129785
|  | Delta | Task 1 | Hirsch | 2020-03-02 | 9 | 2020-03-12 | 8 | 88.89% | 787000 | 727188
|  | Delta | Task 2 | Samora | 2020-03-02 | 10 | 2020-03-13 | 2 | 20% | 228000 | 47880
|  | Delta | Task 3 | McFay | 2020-02-17 | 4 | 2020-02-20 | 0 | 0% | 147000 | 0
|  | Delta | Task 4 | Wood | 2020-02-19 | 8 | 2020-02-28 | 5 | 62.5% | 338000 | 205123
|  | Delta | Task 5 | Ladd | 2020-02-24 | 10 | 2020-03-06 | 3 | 30% | 857000 | 305949
|  | Delta | Task 6 | Hirsch | 2020-02-25 | 6 | 2020-03-03 | 3 | 50% | 602000 | 322371
|  | Delta | Task 7 | Samora | 2020-02-25 | 4 | 2020-02-28 | 2 | 50% | 990000 | 451440
|  | Alpha | Task 1 | McFay | 2020-02-28 | 8 | 2020-03-10 | 3 | 37.5% | 96000 | 32256
|  | Alpha | Task 2 | Wood | 2020-03-02 | 9 | 2020-03-12 | 4 | 44.44% | 513000 | 226233
|  | Alpha | Task 3 | Ladd | 2020-02-20 | 5 | 2020-02-26 | 3 | 60% | 616000 | 401579
|  | Alpha | Task 4 | Hirsch | 2020-02-19 | 3 | 2020-02-21 | 3 | 100% | 817000 | 807069
|  | Alpha | Task 5 | Samora | 2020-02-21 | 7 | 2020-03-02 | 3 | 42.86% | 372000 | 173166
|  | Alpha | Task 6 | McFay | 2020-02-24 | 10 | 2020-03-06 | 2 | 20% | 50000 | 8400
|  | Alpha | Task 7 | Wood | 2020-02-24 | 10 | 2020-03-06 | 3 | 30% | 807000 | 262679
|  | Alpha | Task 8 | Ladd | 2020-02-24 | 3 | 2020-02-26 | 1 | 33.33% | 691000 | 0
|  | Mega | Task 11 | Peter | 2020-03-05 | 3 | 2020-03-09 | 2 | 66.67% | 50000 | 40000
|  | Mega | Task 4 | Hirsch | 2020-03-06 | 2 | 2020-03-09 | 3 | 150% | 500000 | 450000
|  | Build | Task 2 | Samora | 2020-02-25 | 2 | 2020-02-26 | 1 | 50%
|  | Build | Task 1 | McFay | 2020-02-26 | 1 | 2020-02-26 | 1 | 100%
|  | Sun Trade | Task 2 | Hirsch | 2020-02-28 | 3 | 2020-03-03 | 2 | 66.67%
|  | Sun Trade | Task 11 | Michle | 2020-02-03 | 1 | 2020-02-03 | 1 | 100%
Formulas:
End Date = WORKDAY.INTL(Table1[[#This Row],[Start Date]]-1,Table1[[#This Row],[Duration]],1)
DASHBOARD
DATABASE
HELP
CONTACT
SETTING

## Setting
Logo | SETTING
|  | Project Information |  |  | Manager Detail |  |  | TasK Detail
|  | S# | Project Name | Start Date | S# | Project Name | Hire Date | S# | Project Name | Hire Date
|  | 1 | Gemini | 2021-02-17 | 1 | Hirsch | 2020-01-01 | 1 | Task 1 | 2020-01-01
|  | 2 | Orion | 2021-02-17 | 2 | Samora | 2020-01-01 | 2 | Task 2 | 2020-01-01
|  | 3 | Vega | 2021-02-17 | 3 | McFay | 2020-01-01 | 3 | Task 3 | 2020-01-01
|  | 4 | Delta | 2021-02-17 | 4 | Wood | 2020-01-01 | 4 | Task 4 | 2020-01-01
|  | 5 | Alpha | 2021-02-17 | 5 | Ladd | 2020-01-01 | 5 | Task 5 | 2020-01-01
|  | 6 | Mega | 2021-06-25 | 6 | Hirsch | 2020-01-01 | 6 | Task 6 | 2020-01-01
|  | 7 | Build | 2021-06-26 | 7 | Peter | 2020-01-01 | 7 | Task 7 | 2020-01-02
|  | 8 | Sun Trade | 2021-06-27 | 8 | Michle |  | 8 | Task 8 | 2020-01-03
|  | 9 |  |  | 9 |  |  | 9 | Task 9 | 2020-01-04
|  | 10 |  |  | 10 |  |  | 10 | Task 10 | 2020-01-05
|  | 11 |  |  | 11 |  |  | 11 | Task 11 | 2020-01-06
|  | 12 |  |  | 12 |  |  | 12
|  | 13 |  |  | 13 |  |  | 13
|  | 14 |  |  | 14 |  |  | 14
|  | 15 |  |  | 15 |  |  | 15
|  | 16 |  |  | 16 |  |  | 16
|  | 17 |  |  | 17 |  |  | 17
|  | 18 |  |  | 18 |  |  | 18
|  | 19 |  |  | 19 |  |  | 19
|  | 20 |  |  | 20 |  |  | 20
DASHBOARD
DATABASE
HELP
CONTACT
SETTING

## Help
HELP
DASHBOARD
DATABASE
HELP
CONTACT
SETTING

## Contact
CONTACT US
DASHBOARD
DATABASE
HELP
CONTACT
SETTING